## Sheet1
RCA_Number | Title_Description | Issue_start_date | Date_Discovered | stop_gap_date | pop_impacted | Campaigns_impacted | Deliveries_impacted | Impact_category | Issue_Cause_Category | Issue_Cause_System | Issue_Cause_Division_Act | Issue_Cause_Division
RCA_20190919_Pre75_Incorrect_OVIDS | Pre75 Incorrect OVID/Population | 2019-09-19 | 2019-10-02 | 2019-10-04 | 9000 | 1 | 2 | Campaign- Incorrect touch | People | MOPS | COPS and Campaign Dev | COPS
RCA_20191008_ESO_Global_Segment_Coding_Error | Coding Error in ESO Global Segment | 2019-10-08 | 2019-10-08 | 2019-10-09 | 70000 | 1 | 1 | Campaign - Miss Touch | People | MOPS | Campaign Dev | COPS
RCA_20191007_incorrect_Social_Code | Sent incorrect Social Code Volume | 2019-10-07 | 2019-10-09 | 2019-10-14 | 500000 | 1 | 1 | Campaign- Incorrect touch | People and Process | MOPS | COPS | COPS
RCA_20191010_Pre10_New_Used_Over_selection | Pre 10 OTM New and Used over selection | 2019-10-10 | 2019-10-11 | 2019-10-17 | 12000 | 2 | 2 | Campaign- Incorrect touch | People and Process | MOPS | COPS | COPS
RCA_20191112_Used_WK_GoogleHubTest | Incorrect OVID assignment in Used WK for the Google Hub Test | 2019-11-12 | 2019-11-13 | 2019-11-13 | 58000 | 1 | 1 | Campaign-Delayed touch | People and Process | MOPS | COPS | COPS
RCA_20191023_ESO_Global_Segment_Coding_Error | Coding Error in ESO Global Segment2 | 2019-10-23 | 2019-11-22 | 2019-11-22 | 426000 | 44 | 44 | Campaign- Incorrect touch | People | MOPS | Campaign Dev | COPS
RCA_20191115_SL_Equipped_nonEquipped | Service Lane Equipped v. Non Equipped Overlap | 2019-11-15 | 2019-12-04 | 2019-12-06 | 40000 | 2 | 20 | Campaign-Delayed touch | People and Process | MOPS | COPS | COPS
RCA_20191209_GMEO_360L | 360L GMEO T4-T9 issue | 2019-07-01 | 2019-12-09 | 2019-12-11 | 6100 | 6 | 0 | Campaign - Miss Touch | People | MOPS | COPS and Campaign Dev | COPS
RCA_20191209_Pre30_DM_Echo_Dot_Test | Pre 30 DM New Echo Dot Test Incorrect Offer Issue | 2019-12-09 | 2019-12-16 | 2019-12-16 | 169000 | 1 | 1 | Campaign- Incorrect touch | People | MOPS | COPS and Campaign Dev | COPS
RCA_20190920_Highlight_Newsletter_Dual_Deployment | Newsletter Dual Deployment | 2019-09-20 | 2019-11-22 | 2019-11-22 | 1900000 | 1 | 18 | Campaign- Incorrect touch | People | MOPS | EMOPs | EMOPs
RCA_20191206_OEM_Highlights_Partial_Deployment | Highlights Partial Deployment | 2019-12-06 | 2019-12-09 | 2019-12-13 | 3385989 | 1 | 5 | Campaign-Delayed touch | People | MOPS | EMOPs | EMOPs
RCA_20191112_SXM_QUAD_Print_Quality | Gray Shade on GAWB Wave 5 letters | 2019-10-15 | 2019-11-07 | 2019-11-07 | 11000 | 1 | 1 | Campaign- Incorrect touch | Technical | MOPS | DMOPs | DMOPs